## Feb
Date | Description | target | status
16/02/2019 | start of the project in the evening | finding suitable ecommerce template | not done
17/02/2019 | looking for free website templates for getting the idea which can help for creating a ecommerce website | finding suitable ecommerce template | done
18/02/2019 | looking for free website templates for getting the idea which can help for creating a ecommerce website | finding suitable ecommerce template | done
19/02/2019 | in order to looking for free website templates, paper work has been done for home page of the website | paper work for idea | not done
20/02/2019 | try to create a homepage and also looking for a template | create home page | in progress and done
21/02/2019 | try to create a homepage and also looking for a template…. In the evening, start learning WORDPRESS | learn wordpress | in progress and done
22/02/2019 | watching the tutorials to learn WORDPRESS and installing theme and plugins | learn wordpress | in progress and done
23/02/2019 | Working on the theme and Templte and using them in website | use of theme and plugins | done
24/02/2019 | customize the theme in a fine look and as requirement | customize theme | in progress and done
25/02/2019 | customizing the theme but not perfect and find the new theme for the website | find the new theme for the website | done
26/02/2019 | customizing the homepage of the website using the elementor plugin of wordpress | homepage editing | in progress
27/02/2019 | customizing the homepage of the website using the elementor plugin of wordpress | homepage editing | in progress
28/02/2019 | customizing the homepage of the website using the elementor plugin of wordpress | homepage editing | done